## FORGE_Gantt
Week 0 start: |  | (Edit data/gantt.json week0_start)
Project: | FORGE
Owner: | Nathan Herling
Updated:
Week | Phase | Activity | Start | End | Status | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Week 0 | Intro | Course intro, repo bootstrap, mentor sync |  |  | planned
Week 1 | Planning | Scope lock, proposal v1, milestone schedule |  |  | planned
Week 2 | Design / Impl | Architecture sketch, calibration tier scaffold |  |  | planned
Week 3 | Design / Impl | Backend skeleton, data loader, posterior interface |  |  | planned
Week 4 | Design / Impl | Hernandez-Lobato PoC integrated |  |  | planned
Week 5 | Design / Impl | Frontend MVP, demo gallery wired |  |  | planned
Week 6 | Design / Impl | FAIR Universe HiggsML evaluation pipeline |  |  | planned
Week 7 | Design / Impl | Worker / hyperparameter sweep harness |  |  | planned
Week 8 | Design / Impl | Integration pass, end-to-end smoke test |  |  | planned
Week 9 | Testing | Unit + integration tests, calibration checks |  |  | planned
Week 10 | Testing | User-facing testing, bug triage, UX polish |  |  | planned
Week 11 | Write-up | Final paper, iShowcase materials, demo prep |  |  | planned
Week 12 | Deliverables | Final submission, iShowcase, repo freeze |  |  | planned
Legend
Intro
Planning
Design / Impl
Testing
Write-up
Deliverables